## Risks
Handy Test Manager Risk List
Risk ID | Date Identified | Headline | Description | Impact | Likelihood | Magnitude | Owner | Management Plan
1 | 2014-10-10 | Incomplete implementation of computer-assisted scoring | Utilizing computer vision techniques to grade exam responses, which is unfamiliar territory for all members of the team. | 5 | 60% | 3 | Alyssa | Alyssa will be conducting research on computer vision related to this particular activitity. Alyssa will be responsible for troubleshooting problems.
2 | 2014-10-17 | Unsatisfactory integration of QR codes | New technology for all team members. | 2 | 40% | 0.8 | Caitlyn | Conducting initial research and prototypes for QR creation and recognition.
3 | 2014-10-17 | Inexperienced team members | A majority of the team has never worked on a software project of this scale and is unsure of many processes and tools that would be helpful. | 5 | 75% | 3.75 | Chris | Chris will use his expertise in the field to ensure the proper tools are used among team members to streamline the development process.
4 | 2014-10-17 | Poor team member commitment and communication | Conflicting schedules among team members may cause insufficient attendance at planning meetings and laboratories, causing them to fall out of touch with the project. | 4 | 40% | 1.6 | Shawn | Shawn will be communicating with the team regularly to stay abreast of any changes in availability/attendance and work to keep everyone up to date.
5 | 2014-10-17 | Poor time management | Team members may be unable to meet scheduled timeline requirements due to improper estimation of the work required. Lack of productivity between semesters. | 4 | 60% | 2.4 | Shawn | Shawn will generously schedule tasks and monitor the workload of each team member accordingly.
6 | 2014-10-17 | Potential lack of resources | Team iscurrently unable to identify what resources may needed over the course of the project. As such, needs may arise that cannot be fulfilled. | 4 | 25% | 1 | Team | Entire team will keep fellow members notified when they identify a need for resources.
7 | 2014-10-17 | Client availability | Client is an instructor with a heavy course load and may not always be able to respond to the team in a timely manner. | 5 | 15% | 0.75 | Client/Shawn | Shawn will remain the primary contact with the client to limit the amount of messages they receive.
8 | [5 empty] | 0
9 | [5 empty] | 0
10 | [5 empty] | 0
11 | [5 empty] | 0
12 | [5 empty] | 0
13 | [5 empty] | 0
14 | [5 empty] | 0
15 | [5 empty] | 0
16 | [5 empty] | 0
17 | [5 empty] | 0
18 | [5 empty] | 0
Note on E2: RUP: Impact is a numerical value, usually between 0 and 3, the represents the impact to the project if the risk comes true. 3 is a severe impact and 0 is no impact.
Note on F2: RUP: Likelihood is the percentage chance that a risk will occur.
Note on G2: RUP: Magnitude is the result of the multiplication of Impact and Likelihood, providing a joint metric suitable for sorting.